## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAGBARI W/S SCH (TW-I), UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000312/2022-2023 | 1395/CDD | 28/11/2022 | 28/12/2022 | CHANDA ENTERPRISE | 8.26 | 0 | 0 | 1
2 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM 120 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR BAGBARI W/S SCH (TW-II), UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000357/2022-2023 | 1396/CDD | 28/11/2022 | 28/12/2022 | CHANDA ENTERPRISE | 8.26 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BAGBARI, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000289/2023-2024 | 4003193816 | 15/07/2023 | 13/10/2023 | W.B.S.E.D.C.LTD | 3.04 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BAGBARI, Harirampur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000288/2023-2024 | 4003193809 | 15/07/2023 | 13/10/2023 | W.B.S.E.D.C.LTD | 3.29 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Additional Carraige of Gravels for Construction of TW at Bagbari PWSS TW-I, harirampur Block, Dakshin Dinajpur District under CMSD-I, CDD PHE Dte. |  |  | ORD/000476/2022-2023 | 583/CMSD-I(D) | 30/11/2022 | 07/12/2022 | CHANDA ENTERPRISE | 0.59 | 0 | 0 | 100
6 | DAKSHIN DINAJPUR | Harirampur | Central Drilling | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Additional Carraige of Gravels for Construction of TW at Bagbari PWSS TW-II, harirampur Block, Dakshin Dinajpur District under CMSD-I, CDD PHE Dte. |  |  | ORD/000477/2022-2023 | 584/CMSD-I(D) | 30/11/2022 | 07/12/2022 | CHANDA ENTERPRISE | 0.59 | 0 | 0 | 100
7 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Material Requisition To Resource Division |  |  | RTOR000053/2022-2023 | 2882/BD | 06/01/2023 | 06/01/2023 | Resource Division | 14.86 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Material Requisition To Resource Division |  |  | RTOR000040/2023-2024 | 1486/BD | 19/09/2023 | 19/09/2023 | Resource Division | 1.09 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bagbari Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012004) | Assistant Engineer - I | Junior Engineer-01 | ORD/000181/2023-2024 | 2107/MLMD | 05/07/2023 | 02/11/2023 | WEST BENGAL ENGINEERING COMPANY. | 26.29 | 0 | 0 | 82
10 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 249/BD | 21/02/2024 | 21/02/2024 | Resource Division | 11.46 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Additional Quotation For BAGBARI-I PHE |  |  | BILL/03555/2023-2024 | BP-2023-24-559 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 1.31 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Laying of Rising Main, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Bagbari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000008/2023-2024 | 95/BD | 13/04/2023 | 25/06/2026 | CREATION CONSTRUCTION | 199.5 | 0 | 0 | 80
13 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BAGBARI PWSS at Harirampur Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11950 | New | Laying of additional distribution of pipeline for the left out area, construction of approach road, and other allied works within command area of Bagbari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000166/2024-2025 | 2256/BD | 13/11/2024 | 15/03/2025 | RELIABLE CONSTRUCTION | 88.24 | 0 | 0 | 70
Total | [13 empty] | 366.79 | 0 | 0