## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KHAKAR W/S SCH, (TW-I), BLOCK - BANSHIHARI, DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000381/2022-2023 | 1315/CDD | 23/11/2022 | 23/12/2022 | PADMA ENGINEERING & CO. | 14.08 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | HIRING OF DIESEL DRIVEN MOTOR CAB (BS-III & ABOVE) HAVING CONTRACT CARRIAGE PERMIT ALONG WITH DRIVER FOR THE OFFICE OF THE EXECUTIVE ENGINEER, CDD, PHE DTE. |  |  | ORD/000418/2022-2023 | 25/S&WSD | 09/02/2023 | 24/02/2023 | ASHUTOSH DAS & CO | 0.24 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KHAKAR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000267/2023-2024 | 4003193522 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.06 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR KAKHAR W/S SCH (TW-II), BANSHIHARI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000380/2022-2023 | 1306/CDD | 22/11/2022 | 22/12/2022 | MENAKA ENTERPRISE | 13.83 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | Material Requisition To Resource Division |  |  | RTOR000054/2022-2023 | 2873/BD | 06/01/2023 | 06/01/2023 | Resource Division | 11.92 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | Material Requisition To Resource Division |  |  | RTOR000031/2023-2024 | 36/BD | 09/01/2024 | 09/01/2024 | Resource Division | 3.87 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Khakar, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02474/2023-2024 | BP-2023-24-406 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 5.65 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Khakar Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011751) | Assistant Engineer - I | Junior Engineer-01 | ORD/000177/2023-2024 | 2096/MLMD | 04/07/2023 | 01/07/2025 | DILIP MAHATO. | 24.32 | 0 | 0 | 96
9 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | KHAKAR PWSS at Bansihari Block, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/11951 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Kakhar Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000010/2023-2024 | 164/BD | 27/04/2023 | 01/12/2025 | M/S. TRILOCHAN CONSTRUCTION CO. | 199.03 | 0 | 0 | 90
Total | [13 empty] | 277 | 0 | 0