## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Material Requisition To Resource Division |  |  | RTOR000056/2022-2023 | 2880/BD | 06/01/2023 |  | Resource Division | 27.64 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000349/2022-2023 | 1608/CDD | 15/12/2022 | 14/01/2023 | DEY ENTERPRISE | 13.8 | 0 | 0 | 1
3 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCH, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000352/2022-2023 | 1607/CDD | 15/12/2022 | 14/01/2023 | DEY ENTERPRISE | 13.8 | 0 | 0 | 1
4 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (TW-II), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000371/2022-2023 | 1608/ CDD | 15/12/2022 | 14/01/2023 | DEY ENTERPRISE | 13.8 | 10.75 | 77.89 | 0
5 | DAKSHIN DINAJPUR | Bansihari | Central Drilling | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 245 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR SHYAMPUR W/S SCHEME (TW-I), BANSHIHARI BLOCK, UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000372/2022-2023 | 1607/ CDD | 15/12/2022 | 14/01/2023 | DEY ENTERPRISE | 13.8 | 10.59 | 76.74 | 0
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Material Requisition To Resource Division |  |  | RTOR000028/2023-2024 | 835/BD | 14/07/2023 |  | Resource Division | 14.37 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SHYAMPUR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000265/2023-2024 | 4003193516 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 2.77 | 2.77 | 100 | 100
8 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SHYAMPUR, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000266/2023-2024 | 4003194835 | 18/07/2023 | 16/10/2023 | W.B.S.E.D.C.LTD | 2.98 | 2.98 | 100 | 100
9 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Shyampur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011902) | Assistant Engineer - I | Junior Engineer-01 | ORD/000119/2023-2024 | 1125/MLMD | 23/06/2023 | 21/10/2023 | DEVI ENTERPRISE... | 26.57 | 19.19 | 72.22 | 72
10 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Laying of Rising Main, Providing FHTC, Construction of 300 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Shyampur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  | Junior Engineer 1 Sub Division | ORD/000020/2023-2024 | 270/BD | 05/05/2023 | 30/01/2024 | DURJOY MITRA | 204.86 | 25.67 | 12.53 | 35
11 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Supply, delivery and making lighting arrangement at T/W No-I of Shyampur W/S scheme in the District of Dakshin Dinajpur under Malda Mechanical Division P.H.E Dte. |  | Junior Engineer-01 | ORD/002626/2023-2024 | 1049/MLMD | 15/03/2024 | 29/03/2024 | MAA BHABOTARINE ENTERPRISE | 4.39 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 2 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 09/01/2024 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 0 | 0 | 100
13 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Laying distribution pipe line for piped water supply scheme for Shyampur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer Sadar | Junior Engineer 1 Sub Division | ORD/000172/2022-2023 | 3267/BD | 08/02/2023 | 09/05/2023 | MOHANTA BUILDERS | 231.18 | 227.17 | 98.26 | 99
14 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | SHYAMPUR PIPED WATER SUPPLY SCHEME | SM/11962 | New | Supply & Delivery of accesories of Pumping Machinery and installation of Voltage stabilizer and other Electro Mechanical components at T/W No-I & II of SHYAMPUR W/S scheme in the District of Dakshin Dinajpur under Malda Mechanical Division P.H.E Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002625/2023-2024 | 1048/MLMD | 15/03/2024 | 29/03/2024 | MAA BHABOTARINE ENTERPRISE | 3.69 | 1.85 | 50 | 100
Total | [13 empty] | 594.97 | 300.98 | 50.59