## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000789/2023-2024 | 4003195530 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 9.2 | 9.2 | 100 | 100
2 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000790/2023-2024 | 4003196353 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 9.46 | 9.46 | 100 | 100
3 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2881/BD | 06/01/2023 | 06/01/2023 | Resource Division | 8.58 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Amai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000205/2022-2023 | 3509/BD | 04/03/2023 | 01/07/2025 | ASHIT KUMAR DEBSHARMA | 228.04 | 137.33 | 60.22 | 85
5 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Amai Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011883) | Assistant Engineer - I | Junior Engineer-01 | ORD/000339/2023-2024 | 2337/MLMD | 26/07/2023 | 23/11/2023 | DEY ENTERPRISE [HOWRAH] | 25.31 | 20.43 | 80.72 | 80
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1838/BD | 18/06/2024 | 18/06/2024 | Resource Division | 4.6 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Banshihari Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000133/2024-2025 | 1944/BD | 27/09/2024 | 17/10/2024 | RANJAN SARKAR | 5.25 | 0 | 0 | 100
8 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Laying of additional distribution pipeline for the left out area and other allied works for Amai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000193/2024-2025 | 01/BD | 02/01/2025 | 28/03/2025 | CHHAYA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 14.85 | 0 | 0 | 100
Total | [13 empty] | 305.28 | 176.41 | 57.79