## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000789/2023-2024 | 4003195530 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 9.2 | 0 | 0 | 100
2 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Amai PWSS, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000790/2023-2024 | 4003196353 | 20/07/2023 | 18/10/2023 | W.B.S.E.D.C.LTD | 9.46 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Material Requisition To Resource Division |  |  | RTOR000055/2022-2023 | 2881/BD | 06/01/2023 | 06/01/2023 | Resource Division | 8.58 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Amai Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000205/2022-2023 | 3509/BD | 04/03/2023 | 01/07/2025 | ASHIT KUMAR DEBSHARMA | 228.04 | 0 | 0 | 85
5 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Amai Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011883) | Assistant Engineer - I | Junior Engineer-01 | ORD/000339/2023-2024 | 2337/MLMD | 26/07/2023 | 23/11/2023 | DEY ENTERPRISE [HOWRAH] | 25.31 | 0 | 0 | 80
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | AMAI PIPED WATER SUPPLY SCHEME | SM/11963 | New | Material Requisition To Resource Division |  |  | RTOR000004/2024-2025 | 1838/BD | 18/06/2024 | 18/06/2024 | Resource Division | 4.6 | 0 | 0 | 0
Total | [13 empty] | 285.18 | 0 | 0