## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 2885/BD | 06/01/2023 |  | Resource Division | 15.55 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | : Payment for the quotation of PH NO-II of Chakla PWSS under Harirampur CCC |  |  | BILL/03553/2023-2024 | BP-2023-24-557 | 16/02/2024 |  | W.B.S.E.D.C.LTD | 8.46 | 0 | 0 | null
3 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Payment for the quotation of PH NO-I of Chakla PWSS under Harirampur CCC |  |  | BILL/03554/2023-2024 | BP-2023-24-558 | 16/02/2024 |  | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | null
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Payment for the quotation of PH NO-I of Chakla PWSS under Harirampur CCC |  |  | BILL/03554/2023-2024 | BP-2023-24-558 | 16/02/2024 |  | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | null
5 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 250 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Chakla Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000243/2022-2023 | 3922/BD | 30/03/2023 | 25/12/2023 | CALCON CONSTRUCTIONS | 445.61 | 172.87 | 38.79 | 55
6 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1839/BD | 18/06/2024 |  | Resource Division | 10.41 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chakla Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011982) | Assistant Engineer - I | Junior Engineer-01 | ORD/000390/2023-2024 | 2398/MLMD | 28/07/2023 | 24/01/2024 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 28.26 | 0 | 0 | 40
8 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Patun More to Jordighi Road via Badalpur from (chainage 1.70 K.M to 13.50 K.M). |  |  | BILL/00192/2024-2025 | null | 05/09/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 16.99 | 0 | 0 | null
Total | [13 empty] | 536.11 | 172.87 | 32.25