## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 250 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Chakla Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000243/2022-2023 | 3922/BD | 30/03/2023 | 28/07/2026 | CALCON CONSTRUCTIONS | 445.61 | 240.33 | 53.93 | 65
2 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chakla Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011982) | Assistant Engineer - I | Junior Engineer-01 | ORD/000390/2023-2024 | 2398/MLMD | 28/07/2023 | 28/11/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 28.26 | 0 | 0 | 40
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Material Requisition To Resource Division |  |  | RTOR000061/2022-2023 | 2885/BD | 06/01/2023 | 06/01/2023 | Resource Division | 15.55 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Material Requisition To Resource Division |  |  | RTOR000034/2023-2024 | 1839/BD | 18/06/2024 | 18/06/2024 | Resource Division | 10.41 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Payment for the quotation of PH NO-I of Chakla PWSS under Harirampur CCC |  |  | BILL/03554/2023-2024 | BP-2023-24-558 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Patun More to Jordighi Road via Badalpur from (chainage 1.70 K.M to 13.50 K.M). |  |  | BILL/00192/2024-2025 | BP-2024-25-125 | 10/09/2024 | 10/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 16.99 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | : Payment for the quotation of PH NO-II of Chakla PWSS under Harirampur CCC |  |  | BILL/03553/2023-2024 | BP-2023-24-557 | 16/02/2024 | 16/02/2024 | W.B.S.E.D.C.LTD | 8.46 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | CHAKLA Piped Water Supply Scheme at Harirampur Block | SM/12049 | New | Laying of additional distribution pipeline for the left out area, construction of approach road and other allied works within command area of Chakla Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  |  | ORD/000285/2024-2025 | 595/BD | 27/03/2025 | 26/05/2025 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 58.81 | 0 | 0 | 0
Total | [13 empty] | 589.5 | 240.33 | 40.77