## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GURKHAIR PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000786/2023-2024 | 4003201662 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.21 | 3.21 | 100 | 100
2 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 2893/BD | 06/01/2023 | 06/01/2023 | Resource Division | 18.86 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Laying of additional distribution pipeline for the left out area , construction of approach road and other allied works within command area of Gurkhair Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  |  | ORD/000184/2024-2025 | 2474/BD | 19/12/2024 | 17/02/2025 | TRIYA CONSTRUCTION | 38.77 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Laying of distribution pipeline by trenchless method using Horizontal Direct Drilling (HDD) machine at Different PWSS (Daulatpur PWSS, Shyampur PWSS, Patiram PWSS, Sundail PWSS, Brahmangaon PWSS, Gurkhair PWSS, Chakla PWSS) in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 2 | ORD/000170/2023-2024 | 1836/BD | 10/11/2023 | 09/01/2024 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 21.3 | 5.15 | 24.18 | 100
5 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Material Requisition To Resource Division |  |  | RTOR000029/2023-2024 | 29/BD | 09/01/2024 | 09/01/2024 | Resource Division | 8.6 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Material Requisition To Resource Division |  |  | RTOR000070/2023-2024 | 400/BD | 07/03/2024 | 07/03/2024 | Resource Division | 10.32 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Additional quotation for PH-I of Gurkhair PWSS under Harirampur CCC in the District of Dakshin Dinajpur. |  |  | BILL/01824/2024-2025 | BP-2024-25-455 | 23/08/2024 | 23/08/2024 | W.B.S.E.D.C.LTD | 1.22 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Payment for the quotation of New Connection of PH NO-II of Gurkhair PWSS under Harirampur CCC in the District of Dakshin Dinajpur. |  |  | BILL/03724/2023-2024 | BP-2023-24-703 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 2.92 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 200 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Gurkhair Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 Sub Division | ORD/000014/2023-2024 | 190/BD | 28/04/2023 | 17/10/2025 | M/S. ANWESHA ENTERPRISE | 351.67 | 141.26 | 40.17 | 42
10 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | GURKHAIR Piped Water Supply Scheme at Harirampur Block | SM/12050 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Gurkhair Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012011) | Assistant Engineer - I | Junior Engineer-01 | ORD/000394/2023-2024 | 2402/MLMD | 28/07/2023 | 27/11/2025 | ANIMA ENTERPRISE | 26.85 | 19.53 | 72.73 | 100
Total | [13 empty] | 483.71 | 169.15 | 34.97