## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Musan PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000787/2023-2024 | 4003201659 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.59 | 0 | 0 | 100
2 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Musan PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | Assistant Engineer - II |  | ORD/000788/2023-2024 | 4003200276 | 28/07/2023 | 26/10/2023 | W.B.S.E.D.C.LTD | 3.56 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | Material Requisition To Resource Division |  |  | RTOR000060/2022-2023 | 2877/BD | 06/01/2023 | 06/01/2023 | Resource Division | 16.35 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Musan Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000025/2023-2024 | 329/BD | 16/05/2023 | 01/11/2025 | CHIRANJIB DAS | 666.63 | 0 | 0 | 45
5 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | : Additional quotation for PH-II of Musan PWSS under Harirampur CCC in the District of Dakshin Dinajpur. |  |  | BILL/01825/2024-2025 | BP-2024-25-454 | 23/08/2024 | 23/08/2024 | W.B.S.E.D.C.LTD | 1.5 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Musan Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012014) | Assistant Engineer - I | Junior Engineer-01 | ORD/000391/2023-2024 | 2399/MLMD | 28/07/2023 | 29/10/2025 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 28.25 | 0 | 0 | 50
7 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | MUSAN Piped Water Supply Scheme at Harirampur Block | SM/12052 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-04 | ORD/000408/2024-2025 | 3388/MLMD | 28/10/2024 | 28/12/2024 | RAMCHANDRA BASAK | 0.78 | 0 | 0 | 100
Total | [13 empty] | 720.66 | 0 | 0