## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Providing drilling crew and other allied works for construction of Tube Well(250mm x 150 mm x 120Mtrs Depth) by utilising Departmental Machineries for Panchhata W/S (TW I&II) ,Kushmandi Block under Dakshin Dinajpur,CDD,PHE DTE. | Driller In Charge | Junior Engineer | ORD/000446/2022-2023 | 1806/CDD | 04/01/2023 | 03/02/2023 | PADMA ENGINEERING & CO. | 20.01 | 0 | 0 | 100
2 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PANCHHATA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000290/2023-2024 | 4003194048 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 2.48 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Material Requisition To Resource Division |  |  | RTOR000064/2022-2023 | 2896/BD | 06/01/2023 | 06/01/2023 | Resource Division | 15.53 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Material Requisition To Resource Division |  |  | RTOR000043/2023-2024 | 1488/BD | 19/09/2023 | 19/09/2023 | Resource Division | 5.08 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Panchhata Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013076) | Assistant Engineer - I | Junior Engineer-01 | ORD/000183/2023-2024 | 2110/MLMD | 05/07/2023 | 02/11/2023 | ANIMA ENTERPRISE | 28.18 | 0 | 0 | 90
6 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 39/BD | 09/01/2024 | 09/01/2024 | Resource Division | 15.15 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Panchhata, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03236/2023-2024 | BP-2023-24-490 | 30/01/2024 | 30/01/2024 | W.B.S.E.D.C.LTD | 6.21 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | PANCHHATA Piped Water Supply Scheme at Kushmundi Block | SM/12055 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Panchhata Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000001/2023-2024 | 16/BD | 04/04/2023 | 01/02/2026 | ANUGRAH CONSTRUCTION PVT. LTD. | 739.63 | 0 | 0 | 45
Total | [13 empty] | 832.27 | 0 | 0