## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of JARAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000270/2023-2024 | 4003194070 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 2.96 | 2.96 | 100 | 100
2 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of JARAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000271/2023-2024 | 4003194072 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 3.43 | 3.43 | 100 | 100
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Jarail W/S Scheme (TW-I & II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000472/2022-2023 | 1809/CDD | 04/01/2023 | 03/02/2023 | PADMA ENGINEERING & CO. | 20.01 | 14.86 | 74.24 | 100
4 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 2872/BD | 06/01/2023 | 06/01/2023 | Resource Division | 16.94 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Jarail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013052) | Assistant Engineer - I | Junior Engineer-01 | ORD/000455/2023-2024 | 2549/MLMD | 04/08/2023 | 24/10/2025 | M/S PARIMAL DAS. | 26.77 | 19.45 | 72.64 | 90
6 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Material Requisition To Resource Division |  |  | RTOR000055/2023-2024 | 255/BD | 21/02/2024 | 21/02/2024 | Resource Division | 15.12 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2305/BD | 22/11/2024 | 22/11/2024 | Resource Division | 2.5 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Aminpur- Dehaband Road via Kantason, Sarala from (Chainage 0.00 KM to 15.45 Km) |  |  | BILL/00109/2024-2025 | BP-2024-25-81 | 01/07/2024 | 01/07/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 6.91 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 17/10/2024 | KINSHIP CONSTRUCTION | 2.39 | 0 | 0 | 100
10 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 23/10/2024 | GOUTAM SAHA | 2.39 | 0 | 0 | 100
11 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | JARAIL Piped Water Supply Scheme at Kushmundi Block | SM/12056 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Installation of IEP, Pump House, Boundary Wall & Approach Road for implementation of Jarail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000095/2023-2024 | 1088/BD | 09/08/2023 | 26/09/2026 | CHIRANJIB DAS | 715.4 | 404.88 | 56.6 | 30
Total | [13 empty] | 814.83 | 445.58 | 54.68