## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Saraihat Bajedonor W/S Scheme (TW-I & II) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000430/2022-2023 | 1808/CDD | 04/01/2023 | 03/02/2023 | PADMA ENGINEERING & CO. | 20.01 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SARAIHAT BAJEDONOR, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000284/2023-2024 | 4003194057 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 3.95 | 0 | 0 | 100
3 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SARAIHAT BAJEDONOR, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000285/2023-2024 | 4003194061 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 3.76 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Material Requisition To Resource Division |  |  | RTOR000062/2022-2023 | 2874/BD | 06/01/2023 | 06/01/2023 | Resource Division | 32.96 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Material Requisition To Resource Division |  |  | RTOR000033/2023-2024 | 831/BD | 14/07/2023 | 14/07/2023 | Resource Division | 13.98 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Material Requisition To Resource Division |  |  | RTOR000015/2024-2025 | 2308/BD | 22/11/2024 | 22/11/2024 | Resource Division | 2.94 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 460/BD | 18/03/2024 | 18/03/2024 | Resource Division | 10.43 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Instalation of IEP, Pump House, Boundary Wall & Approach Road for implementation of Saraihat Bajedonor Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000232/2022-2023 | 3906/BD | 29/03/2023 | 01/10/2025 | CHIRANJIB DAS | 660.02 | 0 | 0 | 85
9 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | SARAIHAT BAJEDONOR Piped Water Supply Scheme at Kushmundi Block | SM/12060 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Saraihat Bajedonor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013134) | Assistant Engineer - I | Junior Engineer-01 | ORD/000185/2023-2024 | 2111/MLMD | 05/07/2023 | 01/04/2025 | ANIMA ENTERPRISE | 26.98 | 0 | 0 | 100
Total | [13 empty] | 775.03 | 0 | 0