## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Mahipaldighi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013181) | Assistant Engineer - I | Junior Engineer-01 | ORD/000182/2023-2024 | 2108/MLMD | 05/07/2023 | 22/10/2025 | M/S D.G.B. ENTERPRISE. | 28.17 | 19.84 | 70.42 | 90
2 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Installation of IEP, Pump House, Boundary Wall & Approach Road for implementation of Mahipaldighi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000096/2023-2024 | 1085/BD | 09/08/2023 | 26/07/2026 | ASHOK MITRA | 807.96 | 381.86 | 47.26 | 45
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Mahipaldighi W/S Scheme (TW-I & II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000471/2022-2023 | 1805/CDD | 04/01/2023 | 03/02/2023 | PADMA ENGINEERING & CO. | 20.01 | 15.54 | 77.63 | 100
4 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of MAHIPALDIGHI, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000283/2023-2024 | 4003194079 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.5 | 4.5 | 100 | 100
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of MAHIPALDIGHI, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000282/2023-2024 | 4003194078 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.51 | 4.51 | 100 | 100
6 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Material Requisition To Resource Division |  |  | RTOR000059/2022-2023 | 2878/BD | 06/01/2023 | 06/01/2023 | Resource Division | 23.09 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 17/10/2024 | KINSHIP CONSTRUCTION | 2.39 | 0 | 0 | 100
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase - I) | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000146/2024-2025 | 2052/BD | 03/10/2024 | 23/10/2024 | GOUTAM SAHA | 2.39 | 0 | 0 | 100
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Material Requisition To Resource Division |  |  | RTOR000068/2023-2024 | 269/BD | 22/02/2024 | 22/02/2024 | Resource Division | 5.01 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Material Requisition To Resource Division |  |  | RTOR000005/2024-2025 | 1837/BD | 18/06/2024 | 18/06/2024 | Resource Division | 15.68 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MAHIPALDIGHI Piped Water Supply Scheme at Kushmundi Block | SM/12062 | New | Restoration of Udaipur Mahipaldighi road from chainage 0.00 km to 8.00 km under Mahipaldighi PWSS at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00211/2024-2025 | BP-2024-25-135 | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 17.04 | 0 | 0 | 0
Total | [13 empty] | 930.76 | 426.24 | 45.8