## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 2879/BD | 06/01/2023 |  | Resource Division | 19.3 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DILKUNTHI, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02564/2023-2024 | BP-2023-24-459 | 17/01/2024 |  | W.B.S.E.D.C.LTD | 5.35 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DILKUNTHI, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02564/2023-2024 | BP-2023-24-459 | 17/01/2024 |  | W.B.S.E.D.C.LTD | 5.35 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DILKUNTHI, Buniadpur C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02563/2023-2024 | BP-2023-24-458 | 17/01/2024 |  | W.B.S.E.D.C.LTD | 3.02 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Bansihari | Malda Mechanical | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dilkunthi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013332) | Assistant Engineer - I | Junior Engineer-01 | ORD/000351/2023-2024 | 2341/MLMD | 26/07/2023 | 23/11/2023 | ANIMA ENTERPRISE | 26.85 | 9.76 | 36.36 | 65
6 | DAKSHIN DINAJPUR | Bansihari | Balurghat Division | DILKUNTHI Piped Water Supply Scheme at Bansihari Block | SM/12063 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 350 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House for implementation of Dilkunthi Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000029/2023-2024 | 370/BD | 22/05/2023 | 17/03/2024 | M/S. NANDY ENTERPRISE | 689.75 | 0 | 0 | 10
Total | [13 empty] | 749.63 | 9.76 | 1.3