## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Material Requisition To Resource Division |  |  | RTOR000038/2022-2023 | 2903/BD | 06/01/2023 | 06/01/2023 | Resource Division | 17.62 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Khir pukhur (KM/TP -80/1- 80/2) between Mallickpur Hat(MKRH) and Balurghat(BLGT) station for Durlabhpur Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000178/2024-2025 | 2303/BD | 22/11/2024 | 21/01/2025 | M/S. TRILOCHAN CONSTRUCTION CO. | 25.34 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Payment for the quotation of New Connection of PH NO-II of DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00033/2024-2025 | BP-2024-25-60 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 6.51 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Payment for the quotation of New Connection of PH NO-I , DURLABHPUR PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00034/2024-2025 | BP-2024-25-61 | 09/04/2024 | 09/04/2024 | W.B.S.E.D.C.LTD | 3.28 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 01/11/2025 | GHOSH BROTHERS | 2425.67 | 132.82 | 5.48 | 30
6 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Durllabhpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013547) | Assistant Engineer - I | Junior Engineer-01 | ORD/001805/2023-2024 | 3692/MLMD | 29/11/2023 | 24/10/2026 | MERCURY ENGINEERING COMPANY. | 28.26 | 9.31 | 32.96 | 60
7 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Naltahar More to Khaspur BPHC road from 0.00 KM to 5.90 Km, Urgent restoration work of hard shoulder in stretches, under Dakshin Dinajpur Highway Division in the District of Dakshin Dinajpur, for laying of water supply pipe line along PW (Road) Dte. under Balurghat Division PHE Dte |  |  | BILL/00495/2024-2025 |  | 25/03/2025 | 25/03/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.64 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DURLLABHPUR PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12241 | New | Charges for Wayleave/Track crossing by MS Casing Pipeline of 600 mm Dia. (9.5 mm Thick) for passing of MS Carrier Pipeline of 200 mm Dia. for Durlabhpur Piped Water Supply Scheme [SM/12241] under Jal Jeevan Mission between Stn. Mallickpurhat (MKRH) - Balurghat (BLGT) at Km. 80/1-2 at a depth of 1.3 m from ground level of EKI-BLGT section by PHED, Balurghat Division, West Bengal |  |  | BILL/00109/2025-2026 |  | 03/07/2025 | 03/07/2025 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION. | 5.81 | 0 | 0 | 0
Total | [13 empty] | 2527.13 | 142.13 | 5.62