## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Boalder Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013551) | Assistant Engineer - I | Junior Engineer-01 | ORD/000340/2023-2024 | 2338/MLMD | 26/07/2023 | 23/11/2023 | WEST BENGAL ENGINEERING COMPANY. | 26.56 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 2900/BD | 06/01/2023 | 06/01/2023 | Resource Division | 25.3 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Boalder (KM/TP -84/3- 84/4) between Mallickpur Hat(MKRH) and Balurghat(BLGT) station for Boalder Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000180/2024-2025 | 2481/BD | 20/12/2024 | 18/02/2025 | RAY CONSTRUCTION &CO. | 31.41 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Payment for the quotation of New Connection of PH NO-I of Boalder PWSS under Balurghat CCC in the District of Dakshin Dinajpur. |  |  | BILL/03726/2023-2024 | BP-2023-24-700 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Payment for the quotation of New Connection of PH NO-II of Boalder PWSS under Balurghat CCC in the District of Dakshin Dinajpur. |  |  | BILL/03727/2023-2024 | BP-2023-24-701 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOALDER PWSS AT BALURGHAT BLOCK, UNDER BALURGHAT DIVISION P.H.E.Dte. IN THE DIST. OF DAKSHIN DINAJPUR. | SM/12244 | New | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 01/11/2025 | GHOSH BROTHERS | 2425.67 | 0 | 0 | 30
Total | [13 empty] | 2516.22 | 0 | 0