## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | Material Requisition To Resource Division |  |  | RTOR000039/2022-2023 | 2904/BD | 06/01/2023 | 06/01/2023 | Resource Division | 22.22 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Faridpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014480) | Assistant Engineer - I | Junior Engineer-01 | ORD/000452/2023-2024 | 2548/MLMD | 04/08/2023 | 02/12/2023 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 30.21 | 25.22 | 83.48 | 93
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | Laying of additional Distribution pipe line for the left out area and other allied works within command area of Faridpur Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 HQ | ORD/000172/2024-2025 | 2272/BD | 20/11/2024 | 20/12/2024 | M/S. SARKAR CONSTRUCTION | 14.68 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | Material Requisition To Resource Division |  |  | RTOR000058/2023-2024 | 251/BD | 21/02/2024 | 21/02/2024 | Resource Division | 24.98 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | QUOTATION PAYMENT FOR PH NO-1 FARIDPUR PWSS UNDER PATIRAM CCC IN THE DISTRICT OF DAKSHIN DINAJPUR. |  |  | BILL/00205/2024-2025 | BP-2024-25-90 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 8.06 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of FARIDPUR, patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02565/2023-2024 | BP-2023-24-460 | 17/01/2024 | 17/01/2024 | W.B.S.E.D.C.LTD | 6.38 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | FARIDPUR Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12703 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Balurghat Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 2 HQ | ORD/000131/2024-2025 | 1906/BD | 26/09/2024 | 16/10/2024 | R.P. CHOUDHURY CONSTRUCTION. | 8.55 | 2.47 | 28.89 | 100
Total | [13 empty] | 115.08 | 27.69 | 24.06