## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Barakali Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014478) | Assistant Engineer - I | Junior Engineer-01 | ORD/000367/2023-2024 | 2373/MLMD | 28/07/2023 | 24/01/2024 | WEST BENGAL ENGINEERING COMPANY. | 26.56 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 2909/BD | 06/01/2023 | 06/01/2023 | Resource Division | 15.8 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Payment for the quotation of New Connection of PH NO-II of Barakali PWSS under Balurghat CCC in the District of Dakshin Dinajpur |  |  | BILL/03730/2023-2024 | BP-2023-24-697 | 18/03/2024 | 18/03/2024 | W.B.S.E.D.C.LTD | 3.66 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | : Payment for the quotation of New Connection of PH NO-I of Barkail PWSS under Balurghat CCC in the District of Dakshin Dinajpur |  |  | BILL/01070/2024-2025 | BP-2024-25-306 | 05/06/2024 | 05/06/2024 | W.B.S.E.D.C.LTD | 5.56 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 22/02/2025 | GHOSH BROTHERS | 3593.49 | 31.58 | 0.88 | 30
6 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Restoration of Thakurpura - Teor Road from chainage 0.00 km to 1.351 km under Barakali PWSS at Balurghat Block, Dakshin Dinajpur. |  |  | BILL/00441/2024-2025 | BP-2024-25-234 | 27/03/2025 | 27/03/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 12.46 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Patiram Rotary to Trimahini road via Thakurpura (MDR) from ch 0.00 KM to 19.450 KM- Restoration of hard shoulder at different stretches under Dakshin Dinajpur Division P.W.Dte. for laying of pipe line under Balurghat Division, P.H.E. Dte. in the district of Dakshin Dinajpur. |  |  | BILL/00494/2024-2025 |  | 25/03/2025 | 25/03/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR DIVISION, PWD. | 0.32 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BARAKALI Piped Water Supply Scheme at Balurghat Block, under Balughat Division PHE Dte. in the District of Dakshin Dinajpur. | SM/12705 | New | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Barakali Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000176/2024-2025 | 2283/BD | 21/11/2024 | 19/06/2025 | MAYA CONSTRUCTION | 22 | 0 | 0 | 0
Total | [13 empty] | 3679.85 | 31.58 | 0.86