## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2022-2023 | 3490/BD | 03/03/2023 | 03/03/2023 | Resource Division | 20.15 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Kushmandi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014720) | Assistant Engineer - I | Junior Engineer-01 | ORD/000464/2023-2024 | 2554/MLMD | 04/08/2023 | 02/12/2023 | SOVON KUMAR DAS. | 11.46 | 9.71 | 84.74 | 85
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2024-2025 | 876/BD | 03/05/2024 | 03/05/2024 | Resource Division | 33.16 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 31/BD | 09/01/2024 | 09/01/2024 | Resource Division | 15.68 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 250 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000070/2023-2024 | 825/BD | 14/07/2023 | 01/09/2026 | DIPESH BHOWMIK | 691.66 | 352.69 | 50.99 | 60
6 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Kushmandi Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014720) | Assistant Engineer - I | Junior Engineer-01 | ORD/000460/2023-2024 | 2553/MLMD | 04/08/2023 | 29/10/2025 | SUDIP DEY | 24.16 | 20.22 | 83.69 | 83
7 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Repairing of Pump House, IEP Blower room and other allied works for HW site and 2nd TW site of Augmentation of Kushmandi Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer | Junior Engineer Kushmandi | ORD/000170/2024-2025 | 2269/BD | 20/11/2024 | 04/01/2025 | M.A. ENTERPRISE | 19.03 | 0 | 0 | 30
8 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kushmandi Piped Water Supply Scheme | SM/12797 | Augmentation | Payment for the quotation of PH NO-III of Kushmandi PWSS under Kushmandi CCC |  |  | BILL/02720/2024-2025 | BP-2024-25-590 | 10/12/2024 | 10/12/2024 | W.B.S.E.D.C.LTD | 4.49 | 0 | 0 | 0
Total | [13 empty] | 819.78 | 382.62 | 46.67