## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2022-2023 | 3493/BD | 03/03/2023 | 03/03/2023 | Resource Division | 37.69 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Harirampur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014718) | Assistant Engineer - I | Junior Engineer-01 | ORD/000459/2023-2024 | 2552/MLMD | 04/08/2023 | 22/10/2025 | MANIK CHANDRA SAHA. | 24.85 | 19.24 | 77.41 | 78
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 38/BD | 09/01/2024 | 09/01/2024 | Resource Division | 12.81 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Daulatpur-Harirampur-Dehaband Road from (chainage 7.00 K.M to 20.60 K.M). |  |  | BILL/00193/2024-2025 | BP-2024-25-124 | 10/09/2024 | 10/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 17.47 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD(Roads) for Harirampur-Beldangi Road from (Chainage 0.0 K.M to 9.40 K.M). |  |  | BILL/00210/2024-2025 | BP-2024-25-134 | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 19.58 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Harirampur Piped Water Supply Scheme | SM/12798 | Augmentation | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 400 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for Augmentation of Harirampur Piped Water Supply Scheme at Harirampur Block in the District of DakshinDinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000091/2023-2024 | 991/BD | 31/07/2023 | 21/03/2026 | ASHIT KUMAR DEBSHARMA | 635.33 | 227.31 | 35.78 | 55
Total | [13 empty] | 747.73 | 246.55 | 32.97