## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DASUL Piped Water Supply Scheme | SM/12810 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dasul Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014362) | Assistant Engineer - I | Junior Engineer-01 | ORD/000368/2023-2024 | 2374/MLMD | 28/07/2023 | 18/12/2025 | PADMA ENGINEERING CO. | 28.31 | 15.73 | 55.57 | 80
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | New | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 22/02/2025 | GHOSH BROTHERS | 3593.49 | 163.39 | 4.55 | 30
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | New | Material Requisition To Resource Division |  |  | RTOR000036/2022-2023 | 2897/BD | 06/01/2023 | 06/01/2023 | Resource Division | 25.08 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | New | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Dasul Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  |  | ORD/000163/2024-2025 | 2232/BD | 12/11/2024 | 12/12/2024 | ABHIJIT HAZRA | 23.28 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | New | Material Requisition To Resource Division |  |  | RTOR000029/2024-2025 | 2323/BD | 22/11/2024 | 22/11/2024 | Resource Division | 17.3 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DASUL Piped Water Supply Scheme | SM/12810 | New | Payment for the quotation of New Connection of PH NO-I of Dasul PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00037/2024-2025 | BP-2024-25-49 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 2.93 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DASUL Piped Water Supply Scheme | SM/12810 | New | : Payment for the quotation of New Connection of PH NO-II of Dasul PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/00038/2024-2025 | BP-2024-25-50 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 3.32 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DASUL Piped Water Supply Scheme | SM/12810 | New | Patiram Rotary to Trimahini road via Thakurpura (MDR) from ch 0.00 KM to 19.450 KM- Restoration of hard shoulder at different stretches under Dakshin Dinajpur Division P.W.Dte. for laying of pipe line under Balurghat Division, P.H.E. Dte. in the district of Dakshin Dinajpur. |  |  | BILL/00492/2024-2025 |  | 25/03/2025 | 25/03/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR DIVISION, PWD. | 1.13 | 0 | 0 | 0
Total | [13 empty] | 3694.84 | 179.12 | 4.85