## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | New | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 2901/BD | 06/01/2023 | 06/01/2023 | Resource Division | 25.57 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | New | Jack Pushing of M.S. pipe of 200 mm dia. Through 600 mm dia R.C.C. Hume pipe (NP4)/ M.S. pipe by Hydraulic Jacking Technique method across Railway Track near Basanti tala (KM/TP -73/6- 73/7) between Rampur Bazar(RMPB) and Mallickpur Hat(MKRH) station for Bolla Piped Water Supply Scheme in the Disrtict of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. |  |  | ORD/000179/2024-2025 | 2310/BD | 22/11/2024 | 21/01/2025 | M/S. TRILOCHAN CONSTRUCTION CO. | 28.27 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | New | Material Requisition To Resource Division |  |  | RTOR000025/2024-2025 | 2317/BD | 22/11/2024 | 22/11/2024 | Resource Division | 19.99 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOLLA Piped Water Supply Scheme | SM/12811 | New | Payment for the quotation of New Connection of PH NO-II of Bolla PWSS under Patiram CCC in the District of Dakshin Dinajpur. |  |  | BILL/01519/2024-2025 | BP-2024-25-377 | 18/07/2024 | 18/07/2024 | W.B.S.E.D.C.LTD | 3.98 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOLLA Piped Water Supply Scheme | SM/12811 | New | Payment for the quotation of New Connection of PH NO-I of Bolla PWSS under Patiram CCC in the District of Dakshin Dinajpur |  |  | BILL/01520/2024-2025 | BP-2024-25-378 | 18/07/2024 | 18/07/2024 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | New | Implementation of Different Piped Water Supply Scheme namely (1) Bolla (2) Durlabhpur (3) Boaldar (4) Trikul at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000069/2023-2024 | 821/BD | 13/07/2023 | 01/11/2025 | GHOSH BROTHERS | 2425.67 | 0 | 0 | 30
7 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | BOLLA Piped Water Supply Scheme | SM/12811 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bolla Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014315) | Assistant Engineer - I | Junior Engineer-01 | ORD/000605/2023-2024 | 2650/MLMD | 10/08/2023 | 27/04/2026 | M/S. KUNDU CONSTRACTION | 28.39 | 0 | 0 | 80
8 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | BOLLA Piped Water Supply Scheme | SM/12811 | New | Laying of additional distribution of pipeline for the left out area, and other allied works within command area of Bolla Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000195/2024-2025 | 48/BD | 06/01/2025 | 21/05/2025 | M/S PINKI CONSTRUCTION | 31.76 | 0 | 0 | 50
Total | [13 empty] | 2567.38 | 0 | 0