## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHULATAIR, Patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002006/2023-2024 | 4003205877 | 07/08/2023 | 05/11/2023 | W.B.S.E.D.C.LTD | 3.48 | 3.48 | 100 | 100
2 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | Material Requisition To Resource Division |  |  | RTOR000037/2022-2023 | 2902/BD | 06/01/2023 | 06/01/2023 | Resource Division | 28.99 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 246/BD | 21/02/2024 | 21/02/2024 | Resource Division | 20.49 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DHULATAIR, patiram C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02566/2023-2024 | BP-2023-24-461 | 17/01/2024 | 17/01/2024 | W.B.S.E.D.C.LTD | 3.47 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dhultair Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014386) | Assistant Engineer - I | Junior Engineer-01 | ORD/000446/2023-2024 | 2546/MLMD | 04/08/2023 | 08/05/2026 | HANNAN BUILDERS PVT. LTD. | 26.78 | 19.51 | 72.85 | 74
6 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | DHULATAIR Piped Water Supply Scheme | SM/12819 | New | Implementation of Different Piped Water Supply Scheme namely (1) Jangalpur (2) Faridpur (3) Dhulatair at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 HQ | ORD/000068/2023-2024 | 820/BD | 13/07/2023 | 30/06/2026 | R.K. ENTERPRISE | 2125.46 | 345.57 | 16.26 | 55
Total | [13 empty] | 2208.67 | 368.56 | 16.69