## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Anantapur Piped Water Supply Scheme (Zone-I & Zone-II) at Kushmandi Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) (Phase-III) | SM/12846 | Augmentation | Laying of allied pipe line & restoration of damaged pipe line for providing FHTC including other related works for retrofitting of Anantapur PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000251/2022-2023 | 3948/BD | 31/03/2023 | 30/04/2023 | BHASKAR BHOWMIK | 1.1 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Anantapur Piped Water Supply Scheme (Zone-I & Zone-II) at Kushmandi Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) (Phase-III) | SM/12846 | Augmentation | Formal work order for the work of Providing Functional House Hold Tap Connection Under Jal Swapna Programme for Anantpur Zone 1 Piped Water Supply Scheme at Kushmundi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000183/2020-2021 | 504/BD | 25/02/2021 | 26/04/2021 | DIPESH BHOWMIK | 61.21 | 0.76 | 1.24 | 95
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Anantapur Piped Water Supply Scheme (Zone-I & Zone-II) at Kushmandi Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) (Phase-III) | SM/12846 | Augmentation | Acceptance cum work order for the work of Work of Allied pipe Line for FHTC work under Anantapur Zone1 PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Department. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000467/2021-2022 | 152/BD | 28/01/2022 | 04/03/2022 | LOKNATH ENTERPRISE | 9.99 | 9.98 | 99.98 | 100
Total | [13 empty] | 72.3 | 10.74 | 14.86