## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Mulahati Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12962 | New | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. |  |  | BILL/00035/2024-2025 | BP-2024-25-32 | 09/05/2024 | 09/05/2024 | M/S. RPP - INFRASTRUCTURES (JV) | 64.39 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | Ground water Based Mini Pipe Water Supply Scheme (Maximum 100 Households) at Uttar Mulahati Mouza of Harirampur Block in the District of Dakshin Dinajpur. | SM/12962 | New | Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 Household) for 295 nos. villages within 08 nos. Block namely Balurghat, Hili, Kumarganj, Tapan, Gangarampur, Kushmandi, Banshihari & Harirampur in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer - I, MLMD,Assistant Engineer HQ,Assistant Engineer Sadar | je1_malda_me,Junior Engineer (Civil),Junior Engineer - I, MLMD,Junior Engineer 1 HQ,Junior Engineer 1 Sub Division,Junior Engineer 2 HQ,Junior Engineer 2 Sub Division,Junior Engineer 3 HQ,Junior Engineer 3 Sub Division,Junior Engineer Balurghat,Junior Engineer Hili,Junior Engineer Kumarganj,Junior Engineer Kushmandi,Junior Engineer Tapan` | ORD/000178/2022-2023 | 3309/BD | 10/02/2023 | 01/01/2026 | M/S. RPP - INFRASTRUCTURES (JV) | 10454.66 | 8.76 | 0.08 | 55
Total | [13 empty] | 10519.05 | 8.76 | 0.08