## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Pundari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-II] | SM/13019 | Retrofitting | Laying of allied pipe line & restoration of damaged pipe line for providing FHTC including other related works for retrofitting of Pundari PWSS at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000241/2022-2023 | 3924/BD | 30/03/2023 | 14/05/2023 | ABHIJIT HAZRA | 20.77 | 0 | 0 | 90
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Pundari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-II] | SM/13019 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 09/BD | 04/04/2023 | 04/04/2023 | Resource Division | 1.51 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Retrofitting of Pundari Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM) [Phase-II] | SM/13019 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000017/2023-2024 | 841/BD | 14/07/2023 | 14/07/2023 | Resource Division | 0.89 | 0 | 0 | 0
Total | [13 empty] | 23.18 | 0 | 0