## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Hilli | Balurghat Division | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | Material Requisition To Resource Division |  |  | RTOR000065/2022-2023 | 2876/BD | 06/01/2023 | 06/01/2023 | Resource Division | 19.44 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Hilli | Balurghat Division | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | Material Requisition To Resource Division |  |  | RTOR000030/2023-2024 | 35/BD | 09/01/2024 | 09/01/2024 | Resource Division | 5.73 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Hilli | Malda Mechanical | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of PURBA MUSTAFAPUR, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02472/2023-2024 | BP-2023-24-409 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 3.66 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Hilli | Malda Mechanical | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of PURBA MUSTAFAPUR, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02471/2023-2024 | BP-2023-24-408 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.45 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Hilli | Balurghat Division | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | Restoration of Gopalpur Binsira road from chainage 2.00 km to 4.60 km under Purba Mustafapur PWSS at Hili Block, Dakshin Dinajpur. |  |  | BILL/00204/2024-2025 | BP-2024-25-128 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 15.17 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Hilli | Balurghat Division | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 100 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Purba Mustafapur Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer Hili | ORD/000013/2023-2024 | 188/BD | 28/04/2023 | 27/12/2025 | M/S. ANWESHA ENTERPRISE | 237.23 | 0 | 0 | 70
7 | DAKSHIN DINAJPUR | Hilli | Malda Mechanical | PURBA MUSTAFAPUR PIPED WATER SUPPLY SCHEME | SM/13091 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Purba Mustafapur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014637) | Assistant Engineer - I | Junior Engineer-01 | ORD/001801/2023-2024 | 3688/MLMD | 29/11/2023 | 28/12/2025 | MANIK CHANDRA SAHA. | 25.51 | 0 | 0 | 72
Total | [13 empty] | 311.2 | 0 | 0