## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 3491/BD | 03/03/2023 | 03/03/2023 | Resource Division | 44.15 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 400 Cum capacity OHR with 20m Staging Height including Soil Investigation, Repairing and Renovation work of Existing Pump House, Construction of new Pump House, Boundary Wall & Approach Road for implementation of Augmentation of Dhiltail Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000231/2022-2023 | 3904/BD | 29/03/2023 | 09/09/2026 | ASHOK MITRA | 502.17 | 146.51 | 29.18 | 45
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Dhiltail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015236) | Assistant Engineer - I | Junior Engineer-01 | ORD/000445/2023-2024 | 2545/MLMD | 04/08/2023 | 29/10/2025 | M/S SABANA CONSTRUCTION | 10.72 | 8.93 | 83.27 | 70
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Dhiltail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015236) | Assistant Engineer - I | Junior Engineer-01 | ORD/000444/2023-2024 | 2455/MLMD | 04/08/2023 | 13/11/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 25.21 | 13.39 | 53.11 | 70
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 461/BD | 18/03/2024 | 18/03/2024 | Resource Division | 1.5 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Dhiltail Piped Water Supply Scheme in Banshihari Block of Dakshin Dinajpur District. | SM/13829 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000019/2024-2025 | 1312/BD | 22/11/2024 | 22/11/2024 | Resource Division | 13.98 | 0 | 0 | 0
Total | [13 empty] | 597.73 | 168.83 | 28.25