## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 150 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Balurghat | ORD/000203/2022-2023 | 3512/BD | 04/03/2023 | 03/06/2026 | M/S. ANWESHA ENTERPRISE | 379.27 | 209.01 | 55.11 | 40
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Jalghar Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015959) | Assistant Engineer - I | Junior Engineer-01 | ORD/000735/2023-2024 | 2797/MLMD | 17/08/2023 | 28/12/2025 | M/S PARIMAL DAS. | 24.02 | 19.38 | 80.66 | 81
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Providing Functional House Hold Tap Connection in connection with Retrofitting for Jalghar Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000067/2023-2024 | 816/BD | 13/07/2023 | 04/12/2024 | KRISHNA PAUL | 12.2 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2022-2023 | 3492/BD | 03/03/2023 | 03/03/2023 | Resource Division | 16.59 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000022/2024-2025 | 2315/BD | 22/11/2024 | 22/11/2024 | Resource Division | 5.09 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Jalghar Piped Water Supply Scheme. | SM/13830 | Augmentation | Restoration of Balurghat to Laskarhat road from chainage 8.00 km to 20.73 km at BALURGHAT & TAPAN Block, Dakshin Dinajpur. |  |  | BILL/00205/2024-2025 | BP-2024-25-127 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 4.59 | 0 | 0 | 0
Total | [13 empty] | 441.77 | 228.38 | 51.7