## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Hili, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002008/2023-2024 | 4003295116 | 20/12/2023 | 19/03/2024 | W.B.S.E.D.C.LTD | 3.74 | 3.74 | 100 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000082/2022-2023 | 3495/BD | 03/03/2023 | 03/03/2023 | Resource Division | 106.52 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Hili Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015982) | Assistant Engineer - I | Junior Engineer-01 | ORD/000457/2023-2024 | 2550/MLMD | 04/08/2023 | 21/12/2025 | MANIK CHANDRA SAHA. | 28.77 | 22.04 | 76.61 | 77
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Erection of Permanent Type village wise Scheme Information Board at different Piped Water Supply Schemes under JJM as per departmental design and drawing for Balurghat, Hili, Tapan & Kumarganj Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000188/2023-2024 | 2069/BD | 16/12/2023 | 30/01/2024 | M.A. ENTERPRISE | 12.1 | 11.64 | 96.26 | 98
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Dismantling of existing dilapidated 340.50 Cum capacity OHR for facilitating the construction of Proposed OHR under JJM at Head Work Site of Hili Piped Water Supply Scheme at Hili Block, in the District of Dakshin Dinajpur, under Balurghat Division, P.H. Engineering Dte. | Assistant Engineer HQ | Junior Engineer Hili | ORD/000165/2023-2024 | 1633/BD | 10/10/2023 | 24/11/2023 | M/S. S. CONSTRUCTION | 13.38 | 7.69 | 57.46 | 48
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 37/BD | 09/01/2024 | 09/01/2024 | Resource Division | 17.03 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Hili Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015982) | Assistant Engineer - I | Junior Engineer-01 | ORD/000458/2023-2024 | 2551/MLMD | 04/08/2023 | 02/12/2023 | SUBRATA KUMAR DAS. | 11.85 | 10.09 | 85.17 | 80
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Sinking of tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing & Construction of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Hili Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | ORD/000092/2023-2024 | 1026/BD | 01/08/2023 | 01/01/2026 | NILKAMAL BASAK | 630.03 | 257.95 | 40.94 | 35
9 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Hili Piped Water Supply Scheme. | SM/13831 | Augmentation | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Hili & Tapan Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000134/2024-2025 | 1942/BD | 27/09/2024 | 17/10/2024 | M/S. A.D. ENTERPRISE | 3.83 | 1.13 | 29.63 | 100
Total | [13 empty] | 827.24 | 314.29 | 37.99