## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-I), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000408/2022-2023 | 1933/CDD | 31/01/2023 | 02/03/2023 | M/S P P ELECTRICALS | 9.42 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-III), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000407/2022-2023 | 1935/CDD | 31/01/2023 | 02/03/2023 | UNIVERSAL ENTERPRISES | 9.7 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BERAIL W/S SCH (TW-II), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. |  |  | ORD/000409/2022-2023 | 1934/CDD | 31/01/2023 | 02/03/2023 | M/S P P ELECTRICALS | 9.42 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000280/2023-2024 | 4003194083 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000281/2023-2024 | 4003194068 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 2.78 | 0 | 0 | 100
6 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BERAIL, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000279/2023-2024 | 4003194082 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.15 | 0 | 0 | 100
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Material Requisition To Resource Division |  |  | RTOR000067/2022-2023 | 2895/BD | 06/01/2023 | 06/01/2023 | Resource Division | 44.9 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Berail Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013060) | Assistant Engineer - I | Junior Engineer-01 | ORD/000179/2023-2024 | 2098/MLMD | 04/07/2023 | 01/11/2023 | MERCURY ENGINEERING COMPANY. | 41.04 | 0 | 0 | 100
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 252/BD | 21/02/2024 | 21/02/2024 | Resource Division | 25.67 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 2307/BD | 22/11/2024 | 22/11/2024 | Resource Division | 1.02 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Urgent restoration of Shoulder in stretches for laying of Drinking water supply pipeline along PWD Roads for Aminpur- Dehaband Road via Kantason, Sarala from (Chainage 0.00 KM to 15.45 Km) |  |  | BILL/00110/2024-2025 | BP-2024-25-83 | 01/07/2024 | 01/07/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 12.84 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Restoration of Hard Shoulder for Daulatpur-Harirampur-Dehaband Road from 7.00 Km to 20.60 Km under Berail PWSS at Kushmandi Block, in the district of Dakshin Dinajpur. |  |  | BILL/00190/2024-2025 | BP-2024-25-123 | 10/09/2024 | 10/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 7.89 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Berail Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000212/2022-2023 | 3643/BD | 15/03/2023 | 01/11/2025 | S & P ENTERPRISE | 1138.61 | 0 | 0 | 35
14 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | BERAIL Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14101 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Kushmandi Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. (Phase- II) | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000140/2024-2025 | 1951/BD | 27/09/2024 | 17/10/2024 | KINSHIP CONSTRUCTION | 2.39 | 0 | 0 | 100
Total | [13 empty] | 1314.24 | 0 | 0