## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Material Requisition To Resource Division |  |  | RTOR000069/2022-2023 | 2887/BD | 06/01/2023 |  | Resource Division | 40.66 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000444/2022-2023 | 1941/CDD | 31/01/2023 | 02/03/2023 | UNIVERSAL ENTERPRISES | 9.7 | 7.12 | 73.42 | 0
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-I), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000443/2022-2023 | 1939/CDD | 31/01/2023 | 02/03/2023 | M/S P P ELECTRICALS | 9.42 | 6.93 | 73.58 | 0
4 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Lohaganja W/S Scheme (TW-II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000445/2022-2023 | 1940/CDD | 31/01/2023 | 02/03/2023 | UNIVERSAL ENTERPRISES | 9.7 | 7.04 | 72.54 | 0
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000278/2023-2024 | 4003194052 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 3.2 | 3.2 | 100 | 100
6 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000277/2023-2024 | 4003194053 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 4.62 | 4.62 | 100 | 100
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Material Requisition To Resource Division |  |  | RTOR000042/2023-2024 | 1490/BD | 19/09/2023 |  | Resource Division | 3.61 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Material Requisition To Resource Division |  |  | RTOR000046/2023-2024 | 30/BD | 09/01/2024 |  | Resource Division | 24.23 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02536/2023-2024 | BP-2023-24-439 | 10/01/2024 |  | W.B.S.E.D.C.LTD | 2.6 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of LOHAGANJA, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02536/2023-2024 | BP-2023-24-439 | 10/01/2024 |  | W.B.S.E.D.C.LTD | 2.6 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Lohaganja Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013122) | Assistant Engineer - I | Junior Engineer-01 | ORD/000370/2023-2024 | 2377/MLMD | 28/07/2023 | 24/01/2024 | CONCORD ENGINEERING | 40.59 | 18.31 | 45.11 | 91
12 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 266/BD | 22/02/2024 |  | Resource Division | 5.37 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Lohaganja Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000220/2022-2023 | 3821/BD | 23/03/2023 | 17/01/2024 | M/S. KAMAK ENGINEERS & CO. | 1213.03 | 671.59 | 55.36 | 68
14 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Restoration of Mahipal Chourange more to Kantabari road from chainage 0.0 km to 7.0 km under LOHANGANJ PWSS at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00113/2024-2025 | BP-2024-25-85 | 01/07/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 18.15 | 0 | 0 | null
15 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | LOHAGANJA Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14102 | New | Restoration of Mahipal Chourange more to Kantabari road from chainage 0.0 km to 7.0 km under LOHANGANJ PWSS at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00113/2024-2025 | BP-2024-25-85 | 01/07/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 18.15 | 0 | 0 | null
Total | [13 empty] | 1405.64 | 718.81 | 51.14