## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Material Requisition To Resource Division |  |  | RTOR000070/2022-2023 | 2886/BD | 06/01/2023 |  | Resource Division | 31.54 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 120 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR NAHIT W/S SCHEME (TW-I & II), KUSHMANDI BLOCK UNDER DAKSHIN DINAJPUR DISTRICT, CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000413/2022-2023 | 1807/CDD | 04/01/2023 | 03/02/2023 | PADMA ENGINEERING & CO. | 20.01 | 14.32 | 71.54 | 0
3 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Material Requisition To Resource Division |  |  | RTOR000022/2023-2024 | 830/BD | 14/07/2023 |  | Resource Division | 21.25 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Nahit,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000273/2023-2024 | 4003194075 | 17/07/2023 | 15/10/2023 | W.B.S.E.D.C.LTD | 2.89 | 2.89 | 100 | 100
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nahit,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000272/2023-2024 | 4003194074 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 7.31 | 7.31 | 100 | 100
6 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Material Requisition To Resource Division |  |  | RTOR000044/2023-2024 | 1489/BD | 19/09/2023 |  | Resource Division | 3.56 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nahit, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03235/2023-2024 | BP-2023-24-489 | 30/01/2024 |  | W.B.S.E.D.C.LTD | 1.25 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nahit, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03235/2023-2024 | BP-2023-24-489 | 30/01/2024 |  | W.B.S.E.D.C.LTD | 1.25 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 264/BD | 22/02/2024 |  | Resource Division | 1.11 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Nahit Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS | Junior Engineer Kushmandi | ORD/000222/2022-2023 | 3820/BD | 23/03/2023 | 17/01/2024 | ANUGRAH CONSTRUCTION PVT. LTD. | 984.89 | 494.95 | 50.25 | 68
11 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Nahit Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013113) | Assistant Engineer - I | Junior Engineer-01 | ORD/000013/2023-2024 | 748/MLMD | 24/04/2023 | 22/08/2023 | DEY ENTERPRISE.. | 30.2 | 24.48 | 81.05 | 75
12 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Restoration of Kushmandi - Mahipaldighi road from chainage 4.4 km to 11.30 km under NAHIT at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00112/2024-2025 | BP-2024-25-86 | 01/07/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.22 | 0 | 0 | null
13 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | NAHIT Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14103 | New | Restoration of Kushmandi - Mahipaldighi road from chainage 4.4 km to 11.30 km under NAHIT at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00112/2024-2025 | BP-2024-25-86 | 01/07/2024 |  | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.22 | 0 | 0 | null
Total | [13 empty] | 1133.69 | 543.94 | 47.98