## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-I), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000468/2022-2023 | 1936/CDD | 31/01/2023 | 02/03/2023 | UNIVERSAL ENTERPRISES | 9.7 | 7.23 | 74.52 | 100
2 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000467/2022-2023 | 1810/CDD | 04/01/2023 | 03/02/2023 | CHANDA ENTERPRISE | 9.69 | 7.27 | 75.07 | 100
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Manikor W/S Scheme (TW-II), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. |  |  | ORD/000469/2022-2023 | 1937/CDD | 31/01/2023 | 02/03/2023 | UNIVERSAL ENTERPRISES | 9.7 | 7.15 | 73.66 | 100
4 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Material Requisition To Resource Division |  |  | RTOR000068/2022-2023 | 2891/BD | 06/01/2023 | 06/01/2023 | Resource Division | 36.47 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Payment for the quotation of New Connection of PH NO-I of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur. |  |  | BILL/02474/2024-2025 | BP-2024-25-570 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.LTD | 2.98 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Payment for the quotation of New Connection of PH NO-II of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur |  |  | BILL/02475/2024-2025 | BP-2024-25-571 | 14/11/2024 | 14/11/2024 | W.B.S.E.D.C.LTD | 2.93 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Payment for the quotation of New Connection of PH NO-III of Manikor PWSS under Kushmandi CCC in the District of Dakshin Dinajpur. |  |  | BILL/00210/2024-2025 | BP-2024-25-84 | 16/04/2024 | 16/04/2024 | W.B.S.E.D.C.LTD | 2.67 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Restoration of Fatepur - Dehaband Road from chainage 0.00 km to 10.00 km under Manikor PWSS at Kushmandi Block, Dakshin Dinajpur |  |  | BILL/00126/2024-2025 | BP-2024-25-87 | 01/07/2024 | 01/07/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.81 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Restoration of Fatepur - Dehaband Road from chainage 10.00 km to 14.40 km under Manikor PWSS at Kushmandi Block, Dakshin Dinajpur |  |  | BILL/00306/2024-2025 | BP-2024-25-197 | 27/11/2024 | 27/11/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 24.26 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Manikor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013190) | Assistant Engineer - I | Junior Engineer-01 | ORD/000184/2023-2024 | 2109/MLMD | 05/07/2023 | 28/01/2026 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 38.23 | 0 | 0 | 70
11 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Installation of IEP, Construction of Pump House & Blower Room, Boundary Wall & Approach Road for implementation of MANIKOR Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000101/2023-2024 | 1106/BD | 11/08/2023 | 01/12/2025 | GHOSH BROTHERS | 1047.18 | 330.33 | 31.54 | 40
12 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Material Requisition To Resource Division |  |  | RTOR000035/2024-2025 | 134/BD | 21/01/2025 | 21/01/2025 | Resource Division | 18.7 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | MANIKOR Piped Water Supply Scheme at Khusmundi Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14104 | New | Material Requisition To Resource Division |  |  | RTOR000034/2024-2025 | 99/BD | 14/01/2025 | 14/01/2025 | Resource Division | 18.7 | 0 | 0 | 0
Total | [13 empty] | 1236.03 | 351.97 | 28.48