## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Material Requisition To Resource Division |  |  | RTOR000071/2022-2023 | 2890/BD | 06/01/2023 | 06/01/2023 | Resource Division | 39.36 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Baldu Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013519) | Assistant Engineer - I | Junior Engineer-01 | ORD/000349/2023-2024 | 2339/MLMD | 26/07/2023 | 23/11/2023 | DAS ENTERPRISE. | 40.31 | 0 | 0 | 60
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Material Requisition To Resource Division |  |  | RTOR000006/2024-2025 | 1840/BD | 18/06/2024 | 18/06/2024 | Resource Division | 24.82 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Additional quotation for PH-I of Baldu PWSS under Harirampur CCC in the District of Dakshin Dinajpur. |  |  | BILL/01823/2024-2025 | BP-2024-25-456 | 23/08/2024 | 23/08/2024 | W.B.S.E.D.C.LTD | 2.73 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Payment for the quotation of New Connection of PH NO-I of Baldu PWSS under Harirampur CCC in the District of dakshin Dinajpur |  |  | BILL/03662/2023-2024 | BP-2023-24-638 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 3.89 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Payment for the quotation of New Connection of PH NO-II of Baldu PWSS under Harirampur CCC in the District of Dakshin Dinajpur. |  |  | BILL/03663/2023-2024 | BP-2023-24-639 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BALDU Piped Water Supply Scheme at Harirampur Block under Balurghat Division P.H.E. Dte. in the District of Dakshin Dinajpur. | SM/14105 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 600 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Baldu Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000094/2023-2024 | 1087/BD | 09/08/2023 | 21/03/2026 | DIPESH BHOWMIK | 953.1 | 0 | 0 | 50
Total | [13 empty] | 1067.32 | 0 | 0