## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-II) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000428/2022-2023 | 1834/CDD | 06/01/2023 | 05/02/2023 | CHANDA ENTERPRISE | 9.69 | 7.33 | 75.67 | 0
2 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Providing drilling crew and other allied works for construction of tube well (250mm x 150mm x 120 mtrs. depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-I) Kushmandi block under Dakshin Dinajpur district, CDD, PHE Dte. | Driller In Charge | Junior Engineer | ORD/000429/2022-2023 | 1833/CDD | 06/01/2023 | 05/02/2023 | CHANDA ENTERPRISE | 9.69 | 7.38 | 76.14 | 0
3 | DAKSHIN DINAJPUR | Kushmundi | Central Drilling | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm x 120 mtrs. Depth) by utilising Departmental machineries for Chandipur W/S Scheme (TW-III), Kushmandi block under Dakshin Dinajpur District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000442/2022-2023 | 1938/CDD | 31/01/2023 | 02/03/2023 | M/S P P ELECTRICALS | 9.42 | 7.11 | 75.43 | 0
4 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000275/2023-2024 | 4003194056 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 6.1 | 6.1 | 100 | 100
5 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000276/2023-2024 | 4003194055 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 4.86 | 4.86 | 100 | 100
6 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Chandipur, Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I |  | ORD/000274/2023-2024 | 4003194054 | 19/07/2023 | 17/10/2023 | W.B.S.E.D.C.LTD | 7.63 | 7.63 | 100 | 100
7 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Material Requisition To Resource Division |  |  | RTOR000066/2022-2023 | 2892/BD | 06/01/2023 | 06/01/2023 | Resource Division | 27.21 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Material Requisition To Resource Division |  |  | RTOR000035/2023-2024 | 1841/BD | 18/06/2024 | 18/06/2024 | Resource Division | 23.01 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Restoration of Udaipur Mahipaldighi road from chainage 0.70 km to 4.00 km (L/S) under Chandipur PWSS at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00203/2024-2025 | BP-2024-25-130 | 12/09/2024 | 12/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 14.75 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Restoration of Udaipur Mahipaldighi road from chainage 0.00 km to 8.00 km under Chandipur PWSS at Kushmandi Block, Dakshin Dinajpur. |  |  | BILL/00212/2024-2025 | BP-2024-25-133 | 13/09/2024 | 13/09/2024 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 11.36 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Kushmundi | Balurghat Division | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Chandipur Piped Water Supply Scheme at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer ,Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer Kushmandi | ORD/000217/2022-2023 | 3874/BD | 28/03/2023 | 01/10/2025 | ALOK ENTERPRISE | 1145.24 | 377.33 | 32.95 | 15
12 | DAKSHIN DINAJPUR | Kushmundi | Malda Mechanical | Chandipur piped Water Supply Scheme at Kusttmundi gtock, under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur. | SM/14106 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Chandipur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013174) | Assistant Engineer - I | Junior Engineer-01 | ORD/001534/2023-2024 | 2099/MLMD | 04/07/2023 | 20/12/2025 | PADMA ENGINEERING CO. | 38.21 | 24.38 | 63.8 | 63
Total | [13 empty] | 1307.18 | 442.12 | 33.82