## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Improvement of Siala Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Jal Jeevan Mission Programme. | SM/15174 | Augmentation | Installation of IEP, construction of Blower room, surface drain & platform including 03 months trial run for Improvement of Siala Piped Water Supply Scheme at Balurghat Block in District of Dakshin Dinajpur under Balurghat Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer HQ | Junior Engineer 1 HQ | ORD/000032/2023-2024 | 437/BD | 31/05/2023 | 15/07/2023 | ZEOLITE FRESH INDIA | 18.69 | 0 | 0 | 96
Total | [13 empty] | 18.69 | 0 | 0