## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15202 | Augmentation | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for JAHARPUR piped water supply scheme at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." | Assistant Engineer Sadar | Junior Engineer (Civil) | ORD/000006/2020-2021 | 1371/BD | 29/09/2020 | 13/11/2020 | MAA KAMAKKHA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 44.54 | 1.7 | 3.81 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15202 | Augmentation | Acceptance cum work order for the work of Providing left out Functional House Hold Tap connection to make all the villages Swajal Gram under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur. |  | Junior Engineer (Civil) | ORD/000466/2021-2022 | 151/BD | 28/01/2022 | 04/03/2022 | JUVENILE ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 9.99 | 9.73 | 97.38 | 100
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15202 | Augmentation | Erection of Display Board at the entry point of different Swajal Gram (Har Ghar Jal Villages) as per departmental design and drawing in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. (For 78 nos Villages). | Assistant Engineer Sadar | Junior Engineer 1 HQ | ORD/000072/2023-2024 | 869/BD | 24/07/2023 | 23/08/2023 | M/S. A.D. ENTERPRISE | 8.22 | 8.14 | 98.96 | 100
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line in for Retrofitting of FHTC under Jaharpur Piped Water Supply Scheme at Banshihari Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15202 | Augmentation | Ground Water based Mini Piped Water Supply Scheme for Suripukur Mouza i.c.w. Retrofitting of Jaharpur PWSS at Banshihari Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte. | Assistant Engineer RWS,Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer 1 Sadar | ORD/000240/2022-2023 | 3944/BD | 31/03/2023 | 10/12/2025 | SARADA ENTERPRISE | 35.22 | 0 | 0 | 80
Total | [13 empty] | 97.97 | 19.56 | 19.97