## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line for Retrofitting of FHTC under Majhigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15204 | Augmentation | Formal Work Order for the work of "Providing Functional House Hold Tap Connection for MAJHIGRAM piped water supply scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division P.H.Engineering Dte." | Assistant Engineer HQ | Junior Engineer 2 HQ | ORD/000010/2020-2021 | 1375/BD | 29/09/2020 | 13/11/2020 | M/S. S. CONSTRUCTION | 47.43 | 1.9 | 4 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Restoration of Pipe Line for Retrofitting of FHTC under Majhigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Jal Jeevan Mission (JJM). | SM/15204 | Augmentation | Restoration of damaged pipeline and allied works for retrofitting of Majhigram Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 2 HQ,Junior Engineer Balurghat | ORD/000228/2022-2023 | 3854/BD | 27/03/2023 | 11/05/2023 | M/S. R.D. CONSTRUCTION | 21.08 | 21.01 | 99.67 | 75
Total | [13 empty] | 68.51 | 22.91 | 33.44