## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Bartakkigram Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012731) | Assistant Engineer - I | Junior Engineer-01 | ORD/000350/2023-2024 | 2340/MLMD | 26/07/2023 | 23/11/2023 | NUPUR CHANDRA HALDER | 38.61 | 17.94 | 46.47 | 50
2 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Sinking of Tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 500 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Pump House, Boundary Wall & Approach Road for implementation of Bartakkigram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000093/2023-2024 | 1086/BD | 09/08/2023 | 21/03/2026 | DIPESH BHOWMIK | 822.67 | 561 | 68.19 | 65
3 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Material Requisition To Resource Division |  |  | RTOR000049/2022-2023 | 2888/BD | 06/01/2023 | 06/01/2023 | Resource Division | 37.69 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Laying of additional distribution pipeline for the left out area , construction of approach road and other allied works within command area of Bartakkigram Piped Water Supply Scheme at Harirampur Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 2 | ORD/000175/2024-2025 | 2074/BD | 20/11/2024 | 16/03/2025 | BISWARUP SAHA | 56.99 | 0 | 0 | 60
5 | DAKSHIN DINAJPUR | Harirampur | Balurghat Division | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Material Requisition To Resource Division |  |  | RTOR000003/2024-2025 | 1836/BD | 18/06/2024 | 18/06/2024 | Resource Division | 25.78 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Payment for the quotation of New Connection of PH NO-II of Bartakkigram PWSS under Harirampur CCC |  |  | BILL/03665/2023-2024 | BP-2023-24-637 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 3.03 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Harirampur | Malda Mechanical | BARTAKKIGRAM PIPED WATER SUPPLY SCHEME | SM/15483 | New | Payment for the quotation of New Connection of PH NO-I of Bartakkigram PWSS under Harirampur CCC. |  |  | BILL/03664/2023-2024 | BP-2023-24-636 | 06/03/2024 | 06/03/2024 | W.B.S.E.D.C.LTD | 3.04 | 0 | 0 | 0
Total | [13 empty] | 987.81 | 578.94 | 58.61