## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte. | SM/15558 | Augmentation | Special repairing and realignment of existing distribution Pipe Line for Bagduar Piped Water Supply Scheme at Banshihari Block, in the district of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer Sadar | Junior Engineer 1 HQ | ORD/000171/2023-2024 | 1855/BD | 17/11/2023 | 01/01/2024 | ASHIT KUMAR DEBSHARMA | 4.15 | 0 | 0 | 10
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte. | SM/15558 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000039/2023-2024 | 1485/BD | 19/09/2023 | 19/09/2023 | Resource Division | 0.66 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte. | SM/15558 | Augmentation | Payment for the quotation of PH NO-III of Bagduar PWSS under Buniadpur CCC in the District of Dakshin Dinajpur. |  |  | BILL/00746/2024-2025 | BP-2024-25-210 | 22/05/2024 | 22/05/2024 | W.B.S.E.D.C.LTD | 8.84 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Bagduar Piped Water Supply Scheme at Bansihari Block under Balurghat Division PHE Dte. | SM/15558 | Augmentation | Sinking of Tube Well, Construction of Pump House, Laying of Pipe Line, Installation of IEP including 03 months trial run & construction of Blower room, surface drain & platfrom for Source Augmentation of Bagduar Piped Water Supply Scheme at Banshihari Block in District of Dakshin Dinajpur under Balurghat Division, PHE Dte, Govt. of West Bengal. | Assistant Engineer HQ,Assistant Engineer Sadar | Junior Engineer (Civil),Junior Engineer Balurghat | ORD/000233/2022-2023 | 3905/BD | 29/03/2023 | 26/01/2024 | ASHOK MITRA | 37.26 | 0 | 0 | 95
Total | [13 empty] | 50.91 | 0 | 0