## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | SM/16207 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Deulbari PWSS ,Kusmandi C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001875/2023-2024 | 4003270146 | 13/11/2023 | 11/02/2024 | W.B.S.E.D.C.LTD | 3.73 | 3.73 | 100 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | SM/16207 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000036/2023-2024 | 926/BD | 27/07/2023 | 27/07/2023 | Resource Division | 0.66 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | SM/16207 | Augmentation | Source Augmentation of Deulbari Piped Water Supply Scheme comprising of Sinking of One Big Dia Tubewell, Construction of (3.6mtr. X 3.00 mtr.) Pump House and Construction of Boundary wall for 3rd Tubewell Site at Deulbari Mouza, Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer RWS | Junior Engineer 2 | ORD/000236/2022-2023 | 3926/BD | 30/03/2023 | 14/05/2023 | BOSE CONSTRUCTION | 35.56 | 24.88 | 69.97 | 70
4 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Deulbari PWSS at Kushmandi Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | SM/16207 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Deulbari Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016346) | Assistant Engineer - I | Junior Engineer-01 | ORD/000450/2023-2024 | 2547/MLMD | 04/08/2023 | 01/06/2024 | BEE GEE CONSTRUCTION. | 10.9 | 10.34 | 94.83 | 100
Total | [13 empty] | 50.84 | 38.94 | 76.6