## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Nawapara Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16208 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Nawapara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016324) | Assistant Engineer - I | Junior Engineer-01 | ORD/000483/2023-2024 | 2559/MLMD | 04/08/2023 | 02/12/2023 | JIBU SINGHA | 10.01 | 8.26 | 82.47 | 82
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Source Augmentation of Nawapara Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16208 | Augmentation | Source Augmentation of Nawapara Piped Water Supply Scheme comprising of Sinking of One Big Dia Tubewell, Construction of (3.6mtr. X 3.00 mtr.) Pump House and Construction of Boundary wall for 3rd Tubewell Site at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer HQ | Junior Engineer Hili | ORD/000229/2022-2023 | 3876/BD | 28/03/2023 | 23/08/2024 | MOHANTA BUILDERS | 36.78 | 24.55 | 66.75 | 90
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Source Augmentation of Nawapara Piped Water Supply Scheme under Balurghat Division, PHE Dte. | SM/16208 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Nawapara, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02473/2023-2024 | BP-2023-24-407 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 4.62 | 0 | 0 | 0
Total | [13 empty] | 51.41 | 32.81 | 63.81