## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | MARGRAM Piped Water Supply Scheme | SM/16269 | New | Material Requisition To Resource Division |  |  | RTOR000043/2022-2023 | 2907/BD | 06/01/2023 | 06/01/2023 | Resource Division | 26.14 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | MARGRAM Piped Water Supply Scheme | SM/16269 | New | : Payment for the quotation of New Connection of PH NO-II of MARGRAM PWSS under BALURGHAT CCC in the District of Dakshin Dinajpur |  |  | BILL/00032/2024-2025 | BP-2024-25-39 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | MARGRAM Piped Water Supply Scheme | SM/16269 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I&II and making compound lighting arrangement at T/W no. I of Margram (Zone-I&II) Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015069) | Assistant Engineer - I | Junior Engineer-01 | ORD/000480/2023-2024 | 2558/MLMD | 04/08/2023 | 29/10/2025 | GHOSH BROTHERS... | 45.44 | 0 | 0 | 100
4 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | MARGRAM Piped Water Supply Scheme | SM/16269 | New | Implementation of Different Piped Water Supply Scheme namely (1) Margram (2) Barakali (3) Sobrasyampur (4) Mahadipur (5) Uttar Khanpur (6) Dasul (7) Jantigram at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 | ORD/000103/2023-2024 | 1142/BD | 14/08/2023 | 22/02/2025 | GHOSH BROTHERS | 3593.49 | 77.61 | 2.16 | 30
Total | [13 empty] | 3670.2 | 77.61 | 2.11