## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Providing Electrical Equipments with all ancillaries and auxiliaries for 2 x 315 KVA (11KV/0.433KV) Sub- Station at WTP of Kumarganj Eastern Sector under Sub-Surface Water Based Piped Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-07 | ORD/001680/2023-2024 | 3417/MLMD | 01/11/2023 | 31/10/2024 | ORIENTAL ENGINEERING CO. | 201.01 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 1145/BD | 14/08/2023 | 14/08/2023 | Resource Division | 191.42 | 0 | 0 | 0
3 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Material Requisition To Resource Division |  |  | RTOR000038/2023-2024 | 1146/BD | 14/08/2023 | 14/08/2023 | Resource Division | 2202.73 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Material Requisition To Resource Division |  |  | RTOR000045/2023-2024 | 1548/BD | 03/10/2023 | 03/10/2023 | Resource Division | 985.63 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Supply, installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for Distribution Zone-XV & XVII (OHR Site) at Western Sector of Kumarganj Sub-Surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under malda Mechanical division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01,Junior Engineer-07 | ORD/001694/2023-2024 | 3421/MLMD | 01/11/2023 | 31/10/2024 | DEY ENTERPRISE.. | 60.96 | 0 | 0 | 70
6 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Supply, installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for Distribution Zone-I, III & X (OHR Site) at Eastern Sector of Kumarganj Sub-Surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/001692/2023-2024 | 3420/MLMD | 01/11/2023 | 31/10/2024 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 91.39 | 0 | 0 | 70
7 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | Assistant Engineer - I | Junior Engineer-04 | ORD/000055/2024-2025 | 1335/MLMD | 25/04/2024 | 25/06/2024 | RAMCHANDRA BASAK | 0.78 | 0 | 0 | 100
8 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 2304/BD | 22/11/2024 | 22/11/2024 | Resource Division | 61.6 | 0 | 0 | 0
9 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Material Requisition To Resource Division |  |  | RTOR000011/2024-2025 | 1545/BD | 28/08/2024 | 28/08/2024 | Resource Division | 61.6 | 0 | 0 | 0
10 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Paikjhara OHR Site (Zone-XV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03781/2023-2024 | BP-2024-25-6 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 8.62 | 0 | 0 | 0
11 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Azadpur OHR Site (Zone-XII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03783/2023-2024 | BP-2024-25-8 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0 | 0
12 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Quotation for Shifting of 11KV HTOH & LTOH lines at 4(Four)nos OHR site Under Kumarganj Sub Surface in the District of Dakshin Dinajpur. |  |  | BILL/00019/2024-2025 | BP-2024-25-33 | 08/04/2024 | 08/04/2024 | W.B.S.E.D.C.LTD | 9.77 | 0 | 0 | 0
13 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Damodarpur OHR Site (Zone-VIII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03786/2023-2024 | BP-2024-25-11 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 8.54 | 0 | 0 | 0
14 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Tajpur OHR Site (Zone-VI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03788/2023-2024 | BP-2024-25-13 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 8.67 | 0 | 0 | 0
15 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Deor OHR Site (Zone-XVII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03779/2023-2024 | BP-2024-25-4 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 4.4 | 0 | 0 | 0
16 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Brahmanpara OHR Site (Zone-III), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03790/2023-2024 | BP-2024-25-15 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 9.1 | 0 | 0 | 0
17 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Udaypur OHR Site (Zone-XIII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03778/2023-2024 | BP-2024-25-3 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0 | 0
18 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Uthrail OHR Site (Zone-IV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03789/2023-2024 | BP-2024-25-14 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 7.02 | 0 | 0 | 0
19 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Palashi OHR Site (Zone-I), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03776/2023-2024 | BP-2024-25-1 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 4.81 | 0 | 0 | 0
20 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Ujirpur OHR Site (Zone-IX), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03785/2023-2024 | BP-2024-25-10 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 0
21 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Pojahar OHR Site (Zone-XVI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03780/2023-2024 | BP-2024-25-5 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 5.19 | 0 | 0 | 0
22 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Krishnapur OHR Site (Zone-X), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03777/2023-2024 | BP-2024-25-2 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0 | 0
23 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Bhagabatipur OHR Site (Zone-VII), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03787/2023-2024 | BP-2024-25-12 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.67 | 0 | 0 | 0
24 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Lakhankuri OHR Site (Zone-XIV), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03782/2023-2024 | BP-2024-25-7 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 9.43 | 0 | 0 | 0
25 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | W.B.S.E.D.C.LTD Quotation charge at Kulahari OHR Site (Zone-XI), Kumarganj CCC in the dist of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/03784/2023-2024 | BP-2024-25-9 | 04/04/2024 | 04/04/2024 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0 | 0
26 | DAKSHIN DINAJPUR | Kumarganj | Balurghat Division | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Kumarganj block of Dakshin Dinajpur district followed by three (3) months trial run and Five (05) year operation and maintenance. | Assistant Engineer RWS | Junior Engineer 1 HQ,Junior Engineer Kumarganj | ORD/000146/2023-2024 | 1469/BD | 15/09/2023 | 01/03/2026 | ECO PROTECTION ENGINEERS PVT. LTD. | 18555.31 | 0 | 0 | 38
27 | DAKSHIN DINAJPUR | Kumarganj | Malda Mechanical | KUMARGANJ SUB-SURFACE WATER BASED PIPED WATER SUPPLY SCHEME | SM/18434 | New | Providing Eletro-Mechanical Components and Making Compound Lighting Arrangement at ten (10) nos Ground Water Based Piped W/S Scheme at Different Distribution Zone (I to X) for Eastern Sector of Kumarganj Sub-surface Water Based Piped W/S Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01,Junior Engineer-07 | ORD/001681/2023-2024 | 3418/MLMD | 01/11/2023 | 28/12/2025 | EASTERN INDIA SALES & SERVICE. | 136.12 | 0 | 0 | 85
Total | [13 empty] | 22646.15 | 0 | 0