## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Providing Functional House Hold Tap Connection in connection with Retrofitting for Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, P.H.Engineering Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer Hili | ORD/000244/2022-2023 | 3951/BD | 31/03/2023 | 15/05/2023 | SREEMAA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 24.48 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Sinking of tubewell, Laying of Rising Main & Distribution System, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including with Soil Investigation, Repairing of Pump House & Blower Room, Installation of IEP, Construction of Boundary Wall, Construction & Restoration of CC Road for Augmentation of Teor Piped Water Supply Scheme at Hili Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer Hili | ORD/000099/2023-2024 | 1096/BD | 10/08/2023 | 22/10/2026 | M/S. ANWESHA ENTERPRISE | 738.35 | 327.22 | 44.32 | 63
3 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Augmentation of Teor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014550) | Assistant Engineer - I | Junior Engineer-01 | ORD/000489/2023-2024 | 2561/MLMD | 04/08/2023 | 28/08/2024 | UTTAM KUMAR GHOSH | 20.49 | 17.91 | 87.42 | 100
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000078/2022-2023 | 3489/BD | 03/03/2023 | 03/03/2023 | Resource Division | 51.59 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Teor Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. | Assistant Engineer - I | Junior Engineer-01 | ORD/002487/2023-2024 | 812/MLMD | 15/02/2024 | 13/08/2024 | SUDIP DEY | 10.81 | 0 | 0 | 70
6 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000020/2024-2025 | 2313/BD | 22/11/2024 | 22/11/2024 | Resource Division | 15.3 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Tior, Hili C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02476/2023-2024 | BP-2023-24-404 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 11.94 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Tior Piped Water Supply Scheme | SM/18630 | Augmentation | Restoration of Teor - Binsira -Maniko- Bangalipur Road from chainage 0.00 km to 1.142 km under Teor PWSS at Hili Block |  |  | BILL/00364/2024-2025 | BP-2024-25-212 | 17/03/2025 | 17/03/2025 | EXECUTIVE ENGINEER, DAKSHIN DINAJPUR, HIGHWAY DIVISION, P.W.(ROADS) DTE. | 6.62 | 0 | 0 | 0
Total | [13 empty] | 879.57 | 345.13 | 39.24