## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000079/2022-2023 | 3488/BD | 03/03/2023 | 03/03/2023 | Resource Division | 36.7 | 0 | 0 | 0
2 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Kamarpara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014570) | Assistant Engineer - I | Junior Engineer-01 | ORD/000473/2023-2024 | 2556/MLMD | 04/08/2023 | 02/12/2023 | NEOGI ENTERPRISE. | 11.35 | 0 | 0 | 50
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Sinking of Tubewell, Laying of Rising Main, Providing FHTC, Construction of 450 Cum capacity OHR with 20m Staging Height including Soil Investigation, Construction of blower room and Pump House, Renovation of Boundary Wall, Construction of Approach Road and installation of IEP for implementation for Augmentation of Kamarpara Piped Water Supply Scheme at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ,Assistant Engineer RWS | Junior Engineer 1 Sadar | ORD/000100/2023-2024 | 1105/BD | 11/08/2023 | 17/12/2025 | S. DUTTA | 777.83 | 0 | 0 | 35
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 245/BD | 21/02/2024 | 21/02/2024 | Resource Division | 14.77 | 0 | 0 | 0
5 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Payment for the quotation of New Connection of PH NO-III of Kamarpara PWSS under Balurghat CCC in the District of Dakshin Dinajpur. |  |  | BILL/00211/2024-2025 | BP-2024-25-64 | 15/04/2024 | 15/04/2024 | W.B.S.E.D.C.LTD | 3.76 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR |  | Malda Mechanical | Augmentation of Ground Water Based Kamarpara Piped Water Supply Scheme | SM/18631 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, making compound lighting arrangement at T/W no. I of Augmentation of Kamarpara Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014570) | Assistant Engineer - I | Junior Engineer-01 | ORD/000469/2023-2024 | 2555/MLMD | 04/08/2023 | 13/11/2025 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 24.74 | 0 | 0 | 80
Total | [13 empty] | 869.15 | 0 | 0