## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | JANGALPUR PWSS | SM/18632 | New | Implementation of Different Piped Water Supply Scheme namely (1) Jangalpur (2) Faridpur (3) Dhulatair at Balurghat Block in the District of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 3 HQ | ORD/000068/2023-2024 | 820/BD | 13/07/2023 | 30/06/2026 | R.K. ENTERPRISE | 2125.46 | 480.4 | 22.6 | 55
2 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | JANGALPUR PWSS | SM/18632 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Jangalpur Water Supply Scheme in the District of Dakshin Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014518) | Assistant Engineer - I | Junior Engineer-01 | ORD/001667/2023-2024 | 2592/MLMD | 08/08/2023 | 28/12/2025 | DEY ENTERPRISE.. | 41.21 | 37.08 | 89.98 | 95
3 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | JANGALPUR PWSS | SM/18632 | New | Material Requisition To Resource Division |  |  | RTOR000040/2022-2023 | 2905/BD | 06/01/2023 | 06/01/2023 | Resource Division | 42.57 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | JANGALPUR PWSS | SM/18632 | New | Erection of Permanent Type Land Demarcation Board within the Premises of different PWSS at Balurghat Block in the Disitrict of Dakshin Dinajpur under Balurghat Division, PHE Dte. | Assistant Engineer HQ | Junior Engineer 2 HQ | ORD/000131/2024-2025 | 1906/BD | 26/09/2024 | 16/10/2024 | R.P. CHOUDHURY CONSTRUCTION. | 8.55 | 2.41 | 28.12 | 100
5 | DAKSHIN DINAJPUR | Balurghat | Balurghat Division | JANGALPUR PWSS | SM/18632 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 250/BD | 21/02/2024 | 21/02/2024 | Resource Division | 27.23 | 0 | 0 | 0
6 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | JANGALPUR PWSS | SM/18632 | New | Quotation Payment for JANGALPUR PH NO1 under Balurghat ccc |  |  | BILL/03503/2023-2024 | BP-2023-24-522 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 7.93 | 0 | 0 | 0
7 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | JANGALPUR PWSS | SM/18632 | New | Quotation Payment for jangalpur PH No II under Balurghat CCC. |  |  | BILL/03502/2023-2024 | BP-2023-24-523 | 15/02/2024 | 15/02/2024 | W.B.S.E.D.C.LTD | 7.94 | 0 | 0 | 0
8 | DAKSHIN DINAJPUR | Balurghat | Malda Mechanical | JANGALPUR PWSS | SM/18632 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of JANGALPUR, Balurghat C.C.C in the district of Dakshin Dinajpur Under Malda Mechanical Division PHE Dte. |  |  | BILL/02477/2023-2024 | BP-2023-24-403 | 03/01/2024 | 03/01/2024 | W.B.S.E.D.C.LTD | 8.28 | 0 | 0 | 0
Total | [13 empty] | 2269.17 | 519.89 | 22.91