## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Procurement of Chemicals, Consumables & Glasswarswe for 05 nos Water Testing Laboratories under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (PART-C). | Assistant Engineer | Junior Engineer 1 HQ | ORD/000216/2023-2024 | 451/BD | 15/03/2024 | 29/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 9.2 | 9.2 | 100 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Procurement of Chemicals, Consumables & Glasswarswe for 05 nos Water Testing Laboratories under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (PART-A). | Assistant Engineer | Junior Engineer 1 HQ | ORD/000217/2023-2024 | 449/BD | 15/03/2024 | 24/01/2025 | GIYASUDDIN SEKH | 3.09 | 0 | 0 | 90
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Supply of reagent suitable for spectrophotometric analysis of Iron i.c.w. water quality monitoring & surveillance programme for 03 nos Water Testing Laboratories (District Laboratory, Paschim Banga Bigyan Mancha & Molladidghi Sub District Laboratory) under Balurghat Division, PHE Dte. in the district of Dakshin Dinajpur. |  |  | ORD/000320/2024-2025 | 1022/BD | 13/06/2024 | 20/06/2024 | LAB ANALYTICS | 0.82 | 0 | 0 | 0
Total | [13 empty] | 13.1 | 9.2 | 70.19