## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Procurement of Chemicals, Consumables & Glasswarswe for 05 nos Water Testing Laboratories under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (PART-C). | Assistant Engineer | Junior Engineer 1 HQ | ORD/000216/2023-2024 | 451/BD | 15/03/2024 | 29/04/2024 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 9.2 | 9.2 | 100 | 100
2 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Procurement of Chemicals, Consumables & Glasswarswe for 05 nos Water Testing Laboratories under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (PART-A). | Assistant Engineer | Junior Engineer 1 HQ | ORD/000217/2023-2024 | 449/BD | 15/03/2024 | 24/01/2025 | GIYASUDDIN SEKH | 3.09 | 0 | 0 | 90
3 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Supply of reagent suitable for spectrophotometric analysis of Iron i.c.w. water quality monitoring & surveillance programme for 03 nos Water Testing Laboratories (District Laboratory, Paschim Banga Bigyan Mancha & Molladidghi Sub District Laboratory) under Balurghat Division, PHE Dte. in the district of Dakshin Dinajpur. |  |  | ORD/000320/2024-2025 | 1022/BD | 13/06/2024 | 20/06/2024 | LAB ANALYTICS | 0.82 | 0 | 0 | 0
4 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Procurement of Chemicals, Consumables & Glasswarswe for 05 nos Water Testing Laboratories under Balurghat Division, PHE Dte. In the District of Dakshin Dinajpur related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission (PART-B). | Assistant Engineer | Junior Engineer 1 HQ | ORD/000215/2023-2024 | 450/BD | 15/03/2024 | 29/04/2024 | M/S. LAXMI ENTERPRISE | 3.44 | 0 | 0 | 100
5 | DAKSHIN DINAJPUR |  | Balurghat Division | Procurement of Chemical, Consumables & Glassware for 05 Nos Water Testing Laboratories in the District of Dakshin Dinajpur Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission for 01 (One) Year. | SM/19082 | Support-WQMSP | Engagement of Laboratory Personnel including Collection of water samples of different PWSS and testing of water samples with preparation of Test result and other Data Entry in IMIS website etc. including Maintenance of Dakshin Dinajpur District Water Testing Laboratory under Balurghat Division, P.H.E. Dte., in the District of Dakshin Dinajpur [For 03 Months w.e.f. 01/01/2025 to 31/03/2025 ] | Assistant Engineer | Junior Engineer 1 HQ | ORD/000205/2024-2025 | 2541/BD | 20/12/2024 | 20/03/2025 | MOHANTA BUILDERS | 2.38 | 1.57 | 66.18 | 100
Total | [13 empty] | 18.92 | 10.77 | 56.93